## Opn Issues
Sl | Circle | Vendor | Equipment | Operational issues | Remarks | Action by | Open/Close | Target | Circle remarks
1 | AN |  | OSS | Implementation of SMS based BTS outage is not yet commissioned. Generation of 19 reports as per Corporate office- data base to be created. | SMS based BTS outage is configured in Alarm box & given the demonstration to concerned SDE WLL & cleared the issue. Generation of reports are working fine & shown the same to concerned SDE WLL. Will get the confirmation mail from BSNL since they are very busy with CMD visit. | ZTE | Close | Closed
2 | AN |  | MSS | Sleep mode problems against incoming calls reg- if sleep mode comes, Mobile station has to register by manually in MP register of MSC to receive i/c calls. Calls is not getting matured if OG calls are made with +91xxxxxxxx format in CDMA Mobile. | Generally, 3 to 4 days mobiles are not used by subsceribers, As per Standard VLR protection period is 24 Hrs, After that subscriber details will be deleted from VLR. Problem may be due to re-registration process. ZTE Engineer attending this problem, we shall close the same by 30-01-2012 | ZTE | Close | closed and under observations
3 | AN |  | MSS | UN Files generated by Billing Server 2, could not be uploaded to Calcutta main BS. | Problem attended and solved, Confirmation pending from BSNL. | ZTE | Close | Closed
4 | AN |  | Operational | BTS Tester Issue: Radiated power from BTS can not be measured due to faulty Power Sensor and Cable of BTS tester. | Already registered complaint with Agilent, New power sensor and cables to be provided by Agilenent. | ZTE | Open | 15.03.2012
5 | AN |  | Operational | Drive Test Tool (Laptop) supplied by ZTE is not working | It was supplied 2520k and BSNL LOCAL staff using it, It became faulty during the period when their was no AMC. Now ZTE is supporting to rectify it. | ZTE | Close | Closed
6 | AN |  | Operational | The Protocol Analyzer supplied by ZTE is not working. | Its in working condition. | ZTE | Close | NA
7 | AN |  | BTS | The GPS Feeder Cables provided in 12 BTS are faulty. |  | BSNL |  | Details not available with ITI. | 8 Nos. rectified
8 | AN |  |  | Car-Nicobar Repeater, Power Card is faulty to be replaced by ZTE. |  | ITI |  | Repeater Power Card
9 | AN |  |  | Out of 8 Mini Links supplied, 6 are yet to be installed by ZTE. |  | ITI |  | Date to be given by ITI
10 | AN |  | Operational | 32 Power modules sent for repairs, 6 Nos ( 2*25 A & 4*50 A) were returned, 26 Nos yet to be received | 6 modules repaired and returned, 12 rectified courired from gurgaon on 1stfeb12, 3 modulesmunder repair, 11 are under transportation from andaman for repair to Gurgaon. | ZTE | Open | 8 Modules by 20.03.2012. Balance after items are recvd from sites to Port Blair, for further dates.
11 | AN |  |  | Both ACs are not working from the day of installation- at 2 BTS Sites (Aloorang & Calicut). Both ACs are faulty at Car Nicobar(IAF). One AC is faulty at 6 BTS Sites- Baratang Jetty, Billiground, South Creek, Humfrigunj, Aerial Bay & Port Mount. |  |  |  | Team attending AC units in South Andaman. Car Nicobar AC being replaced by New Unit by BSNL.
12 | AN |  | Operational | Both sets of Battery are faulty- at Webi BTS Site and One set is faulty at Humfrigunj. | Batteries are not under AMC. | ZTE | Close | NA
13 | AN |  |  | Infrastructures diverted from UP- UTL- AMC to be signed (10 sites). |  | BSNL |  | TO BE TAKEN WITH UTL / ITI. 28.02.2012
14 | AP | ZTE | MSS |  Maintenance of different servers is very poor. In MSC Hyderabad OU (Osmania University) Servers and KVM switches not attended by ITI / ZTE for the past one year. It is very difficult even to take back up of VLR and HLR data | Hardware fault of all 7 servers are rectified on 5th Jan12, 1 server is having software problem, troubleshooting under progress, 4 KVM switch are sent for repair, will be closed by 15th Feb. | ZTE | Open | 2012-03-25
15 | AP |  | MSS | Preventive maintenance is not at all done by M/s ITI / ZTE as reported by MSC in-charges .Inter changing of Active / standby control cards was not done any where during part of preventive maintenance | Preventive maintenance of the MSCs in AP circle completed for last Quater signed by concerned MSC incharged , Copy of the acknlogement will be provided. Interchanging of active / standby need to be carried out during the off peak hours and requires BSNL authorities to be present. Will be done in the presence of BSNL officials, ZTE is ready to complete the said activity BSNL Circle to confirm the date to perform the activity. | ZTE/BSNL Circle. | Close
16 | AP |  | Operational | Technically skilled engineers should be made available at nearest point to all the MSC s for quick restoration of Hardware faults. Particularly technically efficient person required for attending MSC faults | ZTE trained staff are available in circle to address the Issues, As required by BSNL Co N.W.O the detail list of ZTE staff will be submitted for PAN India. | ZTE | Close | For UTL project, manpower detail provided to UTL.
17 | AP |  | MSS | Threshold monitoring at MSC level is not available. If a subscriber exceeds certain OG call units for eg. 3000 units there should be provision for automatic outgoing barring facility with suitable announcement. Presently this feature is not available | Threshold of billing can be configured on time based and this parameter can be configured starting from 60 mins same already demonstrated to Local BSNL team. | ZTE | Close | Closed
18 | AP |  |  |  CRBT Service is not working in MSC WLL VJ. A/T was rejected |  |  |  | Comverse and OnMobile need to sort the issue.
19 | AP |  | PDSS | Internet is not working in Mobile Hand sets with RUIM | WAP 2 feature enabled Handseta are required i:e Samsung Corby etc, Same had been demonstrated in Kerala,KTK and GJ circles. | ZTE | Close | Closed
20 | AP |  | Operational | Critical / Sufficient spares are not being maintained due to which fault restoration is abnormally delayed | Stocked at ZTE office in HYD. As of now no call logs are pending. | ZTE | Close | Closed
21 | AP |  | LIS | Recently LIS has been shifted to Ernakulam. All features such as FAX, Email are to be tested. | FAX, Email testing is pending same will be demonstrated. | ZTE | Open | 2012-03-18
22 | AP |  | LIS | Live Call Observation is not possible | Subscriber can be put on monitering in LIS, The call can be recorded as well as can be heard by using FanOut option in LIS. | ZTE | Close | Closed
23 | AP |  | BSS | Visual Alarm boxes are not working | 5 Alarm Boxes are having Issues, Same will be replaced by ZTE. | ZTE | Close | 2012-03-31
24 | AP |  | MSS | VPN / UMS services are to be tested at all MSCs | VPN / UMS services are working same will be demonstrated to BSNL circle. | ZTE | Open | 2012-03-31
25 | AP |  | OSS | All MSCs and BSCs are to be connected to OSS | Except Tirupati MSC, bsnl media issue, ZTE and local bsnl working on it. For OU ZTE team alradyy working on it.All other MSCs and BSCs are connected to OSS. | ZTE | Close | Closed
26 | AP |  | BSS | No SMS based fault escalation mechanism is available for quick restoration of faults for 1X BSCc | SMS is sent through the alarm box to all the concerned people's numbers added through the BSC OMC. Same can be configured. The alaram BOX supplied are for MSC's are not fully utilised, Spare alarm BOX can be utilized for BSC-1X alarm escalation by SMS. | ZTE | Open | Waiting for patch
27 | AP |  |  |  FAN,VSWR,GPS antenna faults are pending in many BTSs | No. Only one call log is pending which is not due to this | ITI
28 | AP |  | MSS | It was observed that call forwarding has some problems and is to be attended. Call forwarding is allowed from lower level (local ) to Higher level (STD) | As per BSNL requirement, Forwarding issue is solved with new patch, We have scheduled to upgrade all 73 MSC across PAN INDIA, it shall be expected to complete by Feb 20th. | ZTE | Close | Closed
29 | AP |  | MSS | While interchanging the DDSN card in MPM, Experiencing one way speech problem in Vizag MSC the same was intimated to M/sZTE. It is to be solved | 3 DDSN and 1 SYCK cards are already replaced on 16th Jan 2012 same was informed to SDE Mr. Rajeshwar Rao, No one way speech observed and reported after replacement, Need confirmation from BSNL Circle. | ZTE | Close | Closed
30 | AP |  | BSS | BTS wise Active customers could not be monitored | In BSCB real time number of call is possible as it is mobile so registration detail is not possible. BTS wise active on call customers can be verified. | ZTE | Open
31 | AP |  | MSS | HLR querry tool is not yet installed | Already installed and demonstrated to BSNL long back. MSC details:Vizag : Mr. Rao, Vijaywada: Sunit Laxmi Madam, HYB Madaopur: Mr. Bhaskar, HYB OU: Mr. Ravindar, Trupati: Mr. Ekambaram. | ZTE | Close | Closed
32 | AP |  | BSS | HIRS E1 Flux observation in 1X BSC s is required as it is available in BSSB | 1X BSC does not support the HIRS E1 Flux observation. | ZTE | Close
33 | AP |  | MSS | In OMM servers of HLR and VLR,log files are appending instead of overwriting which is reducing the disk space and also causing inconvenience in deleting old log files | This problem was reported from HYD OU MSC,Auto LOG clearence is already enabled and demonstrated to Mr. Ravinder. ZTE had enabled the same in PAN india all MSC's. | ZTE | Close | closed
34 | ASM | ZTE & ITI | BTS | Restoration of the HW/SW issues relating to WLL BTS & faulty cards by M/s ZTE is very slow.In spite of daily persuasions as many as 29 WLL BTSs have alarms for which one/more BTS sectors are down and BSNL service & Revenue is at stake. Two BTS sites (Chokihola &Dhansiri) are down for more than 6 (six) months due to non supply of required (damaged by rodent cut) cables by M/s ITI / M/s ZTE. | Only 16 faults are docketed. Chokihola & Dhansiri BTS- Rodents have eaten the cables. It will take time to supply the cables. Nogaon SSA already sent requisition to ITI for new cables, ITI to take action and provide new cables to BSNL as we donot have any spare cable- This is physical damage and doesnot come under AMC. BSNL to place the PO for the same. | ITI
35 | ASM |  | LIS | ZTE still to complete the LIS Target Administrator installation work for Assam Circle in spite of repeated reminders. | Work of LIS is under Progress. | ZTE | Open | 2012-04-10
36 | ASM |  | MSS | Call Forwarding restriction to other operators - Still to be implemented in Assam MSCs by M/s ZTE | IN Progress PAN India | ZTE | Open | 2012-04-15
37 | ASM |  | MSS | b. Restriction direct local dialing (w/o prefixing SDCA code) from RUIM nos - Still to be implemented in Assam MSCs by M/s ZTE | DAS configuration need to be changed. We will arrange necessary support for MSC configuration. | ZTE | Open | 2012-04-20
38 | ASM |  | Operational | Several Hard disk faults at Guwahati MSC location are pending for more than 3(three) months. ZTE still to respond. i. OSS Client & CSC PC Hard Disc is faulty since June’11 ii. HLRDB Backup Server Mother Board is Faulty since Oct’11. iii. KVM Switch of BSC-OSS is faulty since July’11 iv. HLROMM Hard Disk Faulty since 11-12-11. | New Hard disk already Ordered, KVM switch-10th Feb 12 | ZTE | Close
39 | ASM |  | Operational | There batteries of Guwahati MSC 30 KVA UPS are faulty for three months and response from M/s ITI/ M/s ZTE is still awaited | Isuue does not come in under AMC project. | ZTE | Close | NA
40 | ASM |  | OSS | Several issues relating OSS are still to be resolved by M/s ZTE. • MSS Jorhat Router is not working since Aug’11 • CNO Report not available for Nagaon 1X BSC & Barpeta Rd.BSCB • BTS status not getting updated for Silchar, Tezpur & Dibrugarh 1X BSCs | Nagaon 1X BSC is connected to OSS and when media is having problem then only reports are not readily available. & Barpeta Rd.BSCB media fluctuation | ZTE | Open | 2012-03-27
41 | ASM |  |  | DTI board termination work under 19.2L project - ZTE still to complete the work at Guwahati MSC site | Cables misplaced from bsnl office. Bsnl to arrange cables
42 | BR |  | LIS/MSC | WAP/WAP 2 function not demonstrated. | WAP/WAP 2 feature are not presently available in BSNL CDMA network,To avail the same BSNL need to Install WAP server in the network. ZTE hereby undertake that whenever the said function is Implemented in BSNL CDMA network same can be Intercepted and demonstrated. In view of above relaxation may be porvided. |  |  | Closed
43 | CG | ZTE & ITI |  | Spare cards for AMC of MSC,BSC BTS( Specially Micro BTS) is yet not supplied by M/s ITI & M/s ZTE | Spares supplied as per PO. Acknowledgement is available | ITI |  |  | Spares supplied as per PO. Acknowledgement is available
44 | CG | ZTE & ITI | Operational | Posting of proper manpower at MSC at CG Circle by m/s ITI & M/s ZTE because only Single engineer from ITI and ZTE is posted at Chhattisgarh Circle. | ZTE trained staff are available in circle to address the Issues, As required by BSNL Co N.W.O the detail list of ZTE staff will be submitted for PAN India. Depending on requirement, manpower will be made available by ITI from adjacement MP circle. | ZTE | Close
45 | CG | ZTE & ITI | Operational | Supply of cards after repairing is very late by M/s ITI & M/s ZTE. |  | ZTE | Close | R&R time will be 7 days after receipt of spares.
46 | CHTD |  | MSC/OSS | MSC 50 K to 100 K - OSS A/T pending | Two reports form 16 Approved MSC reports by BSNL Co office are not available, Due to which AT officer is not starting the AT. It is requested that these two reports shall be relaxad so the remaining available reports can be demonstrated and AT shall be completed. | ZTE | Close | 30-03-2012
47 | CHTD |  | Operational | DG sets for BTSs -AT pending | ZTE had installed 3 earth pits where as BSNL AT officer was asking 4 earthpits,Where as other vendors in CHTD had povided 1 earthpit and connected all equipments Body and netural. ZTE had given the request letter to consider the three earth pits alone , Since the measure earth value is within the limits. BSNL Circle is reviewing the request given by ZTE. AT can be completed within 25 days of the required clearance. | ZTE | Open | DG AT scheduled from this week. Expected to be closed by 31.03.2012
48 | CHTD |  | LIS | L I server - Shifting to Ernakulam is completed. A/T is pending | Only 1 AT point (MDN issue) is pending - Not Possible - Clarification provided. Target Activation can be done only from LIS client and by authorized person, He should have the details of Party Identity - MDN, ESN and IMSI. they need to maintain these details. Even if we provide MDN option for interception, desired results cannot be obtained. what is the use of such interception? All CDMA operators are using IMSI for Data call interception. | ZTE | Open | MSC Upgradation planned on 07.03.2012. After this, it can be tested. Target: 31.03.2012
49 | GJ |  |  | WIN: -
50 | GJ |  | WIN | 1.Call forwarding LRN base 2.Code wise charging through ctopup. 3.Multi FNS group required 4.CTOPUP recharge of portin number. 5.The SMS STV count once given in IN does not differentiate between local or std or isd. 6.Coustmer in FNS & free call group are able to call within group even if balance is -ive. 7.MTS Roaming testing is pending as we get number without 91 is MSC send wrong Nature value. 8.Data STV is not working if balance in his account is < .5 rs. 9.In IVC SSTP link master/standby is not working. 10.In IVC Query of Recharge log is not according to date, denomination ,circle wise. | 1. As discussed in 24 -25 Nov2011 meeting ZTE will release IN New patch on April-2012 2. This is a new Requirement.Commercial to be discussed. 3. This is a new Requirement.Commercial to be discussed. 4. This is not ZTE issue.This is PYRO issue. 5. Supported by the system. Already explain and given the procedure to Vadodra team,After Implementaion by the said procudure the SMS STV counts for Local,STD and ISD can be differinated. Vadodara BSNL is not accepting the procudure/solution given by ZTE. 6. Current Version does not support. 7. MTS need to send 12 Digit number because BSNL/ZTE WIN only cc+mobile number, BSNL to arrrange the meeting for getting all Issues resolved which are being faced. We have already share the deatils with MTS where we need 12 digit number as per MTS asking.Now MTS checking this issue. 8. Solved on 17-Jan-2012. Also demostrate to BSNL Vadodara. 9. Solved 10. This is a new Requirement. | ZTE | Close
51 | GJ |  |  | IFWT: -
52 | GJ |  |  | In accordance with the DGM(NWP-CDMA), Corporate office , New Delhi letter No. 69-22/2008-CDMA)/Vol-II Date d 30-12-2010, commercial analysis was to be carried out for entering into AMC. No proper commercial analysis guidelines are mentioned in the letter. There are cases where cost of AMC is more than the replacement cost of IFWT/FWT. In that case if we do not enter into AMC then faulty FWTS will keep on accumulating and decision regarding scrapping such FWTs would need to be taken since there life would not be over . Otherwise rate for repair of individual FWT may be finalized with the vendor . A letter for the same is already sent (copy attached) |  | BSNL
53 | GJ |  |  | Roaming with MTS: -
54 | GJ |  | WIN/SMS | For pre paid voice calls the required digits profile is 9191841xxxxx instead it comes 91841xxxxx so calls are getting failed. For MO SMS issues are with MTS MSC GT , SMC Pune not able to recognize MCC (Mobile country code). For MT SMS DPC+SSN routing is not successful to MTS MSC New Delhi. MSC supports call forward restriction to private operator on level base but it should be on LRN base so that forwarding of calls from BSNL to Private operators can not be prevented. | ZTE end is resolved. MTS need to send 12 Digit number because BSNL/ZTE WIN only cc+mobile number, BSNL to arrrange the meeting for getting all Issues resolved which are being faced. We have already share the deatils with MTS where we need 12 digit number as per MTS asking.Now MTS checking this issue. For SMS issue we already finish all cofiguration at SMSC end. Need MTS check configuration at their end.Pending from MTS end.We have already submit the Message to STP. | ZTE | Close | closed
55 | GJ | Teracomm |  | Teracomm had supplied Huawei make NIC-321 & NIC-325 but he had not provided drivers of these devices supporting with Windows Xp 64 bits , windows7 -64 bits & Linux operating system. Due to this problem, many customers had closed their NIC connections resulted in financial loss to BSNL & also loss of Customers goodwill towards BSNL. Similarly all Operators who are supplier of Data Card, FWTs & IFWTs should provide drivers supporting with all Operating system & configuration tools also need to be supplied. | Infra faults only can be booked | Not Applicable
56 | HAR | ZTE | LIS | 1. M/s ZTE has to provide end to end connectivity and configuration for extraction of IRI( intercepted report information) from CDMA LIS (Lawful interception server) to CMS server through MPLS being installed at Ambala by CDOT as per instruction from TERM Cell. As a standby LIS is also to be extended to the clients installed at both the MSC ( at Hisar and Karnal). At present CDMA LIS Ghaziabad has been extended upto Centralized Monitoring Server, Ambala on single E1. Testing by fixing the target at CMS server and through clients at both the MSC has not been done so far. M/s ZTE is being pursued for early completion of project in coordination with M/s CDOT and M/s Variant | Already Connectivity estableshed with Ghaziabad MSC and Ambala CMS system, testing under progress. Verint team is working on content pushing in FTP server. | Verint
57 | HAR |  |  | 2. M/s ITI has not provided any portal for the booking of faults of Core equipment due to which faults of IFWTs and core equipments remain faulty for long time which are supplied in Haryana Circle against PO No. CE/PO/009/2005-06 dated 27-01-2011, CE/PO/017/2006-07 dated 16-03-2007, CE/PO/016/2004-05, CE/PO/001/2005-06 dated 25-05-2005, CE/PO/008/2005-06 dated 28-12-2005, CE/PO/019/2002-03 dated 27-01-2003 and PO-CE/PO/010/2005-06 dated 29-11-2006. | Infra faults only can be booked | ITI
58 | HAR |  |  | 3. Haryana Circle has signed AMC with M/s ITI against the mentioned POs:- a. CE/PO/016/2004-05 & CE/PO/001/2005-06 dated 25-05-2005 for 5070 IFWT sets signed on 14-10-2008. b. CE/PO/017/2006-07 dated 16-03-2007 for 4800 IFWT sets signed on 23-01-2010. c. CE/PO/009/2005-06 dated 27-01-2011 for 9855 IFWT sets signed on 20-05-2010. But, as per field reports M/s ITI is not attending the faulty IFWT sets. | ITI has not received details of faulty IFWTs. | ITI
59 | HAR |  | BTS | 4. GPSTM connector is faulty at Gurawada Site in Rewari SSA, for which M/s ITI /ZTE(under 630k line project) is intimated many times but still the connector has not been replaced. | 4 GPSTM connector's are received at HAR, Will be replaced by 25th Jan 2012. | ZTE | Close | closed
60 | HAR |  | Operational | 5. Three HP servers (i.e. Map server, HLR O&M server and VLR ADC server under 630K line project) and four hard disks (3 cluster hard disks and 1 VLR hard disk) are lying faulty in MSC Hisar. Repairing of the same is required from M/s ITI/ZTE. | Servers rectified on 17-01-12 and was informed to SDE MSC Sunita Araora Madam, 2 Hard disk supplied to hisar , 2under process | ZTE | Close | closed
61 | HAR |  | bts | 6. One PCM cable (under 630K line project) is lying faulty at Satrod BTS site. Action is to be taken by M/s ITI/ZTE. | Cable is in transportation, to be replaced by 30th Jan 2012 . | ZTE | Close | closed
62 | HP | ITI |  | Cards given to M/s ITI are not repaired. Oldest card handed over to ITI was in the month of JUN-2010. 34 faulty cards were handed over to ITI up to DEC-2010. 58 cards are handed over to ITI from JAN-2011 to AUG-2011. All the cards are pending with ITI for repair. | 20 cards are sent by ITI remaining 28 cards will be sent in one or two days by ITI. Rest of card has to be sent by ZTE. | ITI |  |  | ITI sent all 48 cards. Now cards are pending from ZTE end. As for remaining cards there is despute in between ZTE and ITI.
63 | HP | ITI | Operational | No spare cards are available with M/s ITI. Once a BTS card gets faulty, it is arranged by it from Bangalore. Fault rectification time is thus excessively high. | 20 cards sent by ITI and 28 cards will be sent. | ZTE | Close | NA
64 | HP | ZTE & ITI | Operational | Only one engineer each is posted in HP by M/s ITI and ZTE. Many times these engineers are unavailable due to leave/ illness/ personal reasons. During such times, faults remain un-attended for weeks. Also one engineer each is insufficient to handle faults in CDMA Network in HP Circle. More trained manpower is required. | ZTE enggs are present in HP and resolving the problems as and when it is reported , As of now out of 6, 2 rectified, 4 under process. | ZTE | Open | 20-03-2012
65 | HP | ZTE & ITI |  | As on date 4 dockets are pending for more than three months, six dockets are pending for more than one month and four dockets are pending for less than one month. Average fault rectification time during last one year by M/s ITI is 28 days and by M/s ZTE is 24 days. | 7-02-2011 | ITI |  | 20-03-2012 | Closed
66 | HP | ZTE | BSS | Two BSCs are not integrated to OSS till date. Dharamshala BSC was integrated but login to this BSC is not working through OSS and reports are also not fetched. | ZTE working on it. | BSNL | Open | 2012-02-25 | Closed
67 | HP | ZTE | BSS | BTS gets down when main CHM card becomes faulty. | If main CHM card is getting faulty then second CHM will autmotaically recover the services. It was very rarely observed that if some CE of main CHM gets faulty then call will get effeected.Solution is to block faulty CE in BSC of that BTS then call will land in second CHM. | ZTE | Close | NA
68 | HP | ZTE | Comverse | Postpaid/ limited plan customers are not able to check their data usage. |  | Comverse |  |  | Closed
69 | JHK |  | MSS/Comverse | 1) HLR Issue: when query of any number is made and then pop windows comes saying “ Modified Successfully” even no modification was done. | No issue with the system,Complete provisioning taken care by comverse B&CCS, during query database will get refresh, hence it will popup this message. It will not have any impact on any service. | ZTE | Close | Closed/Reply submitted
70 | JHK |  | BSS | 2) BSC Issues : a) FAX not working in 630K EVDO BSC b) OSS Report Problem (i.e. Report is not generated). c) Unrestored BTS Alarm when saved, saves one BTS alarm only in BSC-1 and BSC-2 (i.e. 630 K Project BSC) d) Some EVDO BTSs have no data flux in some PCMs even PCMs are OK. | a) Patch is Implemented will be demonstrated to BSNL by 10th Feb 2012. B) OSS reports are being generated the same was demonstrated to SDE Mr. Pankaj. C) All BTS need to be selected while saving the alarms. D) Patch implemented, need to demonstrate to bsnl. | ZTE | Close | closed
71 | JHK |  | BTS | 3) BTS Issues: a) Chip is not installed in GPSTM Card in many BTSs as a result GPSTM Resets. Thus hampering call and 1X data. b) Temperature Sensor and Smog Sensor are either not installed or not working in many BTSs. c) Faulty Card (such as GPSTM,CCM,RFIM,CHM,HPA,TRX etc) problem in many BTSs under warranty and AMC. | GPSTM chip: Work is under progress in circles wherever it is pending by 28th Feb 2012. (b)Temperature sensor: Not docketed on ITI website, Circle to register the call log. (c )Out of the 15 faults docketed none of these cards appear to be faulty. ZTE will resolve it alarms, ITI need to rectifyalarms of 630K PO. | ZTE | Open | Will be close at earliest.
72 | JHK |  | LIS | LIS Migration from Vadodara to Kolkata Pending. | closed | ZTE | Close | closed
73 | JHK |  | MSS | CRBT Pending points still not tested. | Need pending point list from BSNLif CRBT issues belongs to ZTE. | ZTE | Open
74 | JHK |  | MSS | pESN and IMEID still not tested. | Completed. ATC and commissioning certificate received | ZTE | Close | Closed
75 | JHK |  | MSS | RUIM Configuration to restrict call without area code. | DAS configuration need to be changed. To be completed by 15th Feb 2012. | ZTE | Close | closed
76 | JHK |  |  | AMC for 2520 K was signed on 4.8.11. Out of 133 BTSs AMC of only 98 BTSs were done to non-availability of ATC for remaining BTSs. M/s ITI Ltd had promised to complete pending A/T by 30.9.11 so that all the BTSs may be included in AMC . Till date all ATCs are still pending as a result no AMC support is available for these BTSs and is affecting QoS of CDMA network. No firm commitment from ITI | Matter has been told to DGM ITI Mr. Biswas also but till now no action has been taken from ITI. | ITI |  |  | Closed
77 | JHK |  | Operational | A lot of equipment like Protocol Analyzer, BTS Tester, Repeters (RF+OF), CSC Terminals, N-BSNL shelters etc ate either not installed or A/T not done. These equipment were excluded from AMC agreement. Still bills for 30% and 20% have been submitted for payment without any clarification for processing the bills. |  | ZTE/ITI | Open
78 | JHK |  |  | The faults are being booked regularly on sites http://111.93.135.186/cdmabg & http://cdma.itiltd-india/cdmabg but still rectification rate of faults is very poor. | As on date only 15 faults are pending. | ITI |  |  | Closed
79 | JHK |  |  | Non-replacement of faulty Cards: - A lot of BTSs remain down due to non-availability of spare cards for rectification. The turn around time of repair of cards is very high as a result BTSs remain down for weeks. | As per PO all spares are supplied under acknowledgement. | ITI |  |  | Closed
80 | JHK |  | Operational | Acute shortage of BTS Maintenance Engineer: - Hardly one or two persons are available in Jharkhand for attending BTS faults. No ZTE Engineer is available in MSC Ranchi. All ZTE Engineers have been shifted out of BSNL project. | As required by BSNL Co N.W.O the detail list of ZTE staff will be submitted for PAN India. | ZTE | Close | For UTL project, manpower detail provided to UTL.
81 | JK | ZTE | BSS | It is intimated that Subscribers of EVDO data services of J&K Circle are often complaining about the perceivable reduction in down load speed. On analyzing the complaints it is noticed that all these Customers were using the services since 2009 and are having better download speeds. During the November 2009 the existing two 50 K BSCBs (one each at MSC Jammu and Srinagar ) were upgraded to Type -2 under 19.2 Lakhs project and M/s. ZTE has limited the speed as per the clause 21.2.4 of PO. Due to this the down load speeds that were available to Customers prior to up gradation were no longer available. As per the referred clause of PO the peak throughput between BTS and BSCB will be 3.96 Mbps/BTS and if the number of simultaneous users per BTS is 24, then the average speed per user will be limited to 150 Kbps only. In J&K circle there is huge demand of EVDO Data Cards. In Srinagar MSC there are 17 EVDO BTSs with 2150 users and in Jammu MSC there are 18 EVDO BTS with 2029 users. In some areas the simultaneous users may cross 60 per BTS, resulting download speed less than 100 Kbps. Due to poor download speed the subscribers have started disconnecting the EVDO data cards and are migrating to Other operators . In this connection it is requested to direct the M/s. ZTE to upgrade the existing BSCBs at MSC Srinagar & Jammu so that peak throughput between BTS and BSCB will be 8 Mbps and enhance the down load speeds per User in EVDO BTSs. Case already been taken up with Corporate Office vide letter no. Genl/Corr/WLL/2010-11/6 Dated 11-2-2011 | The downloading speed has been tested on various BTS sites & same has been analyzed by ZTE Technical team & the reason for poor downloading speed is loading of BTS. Same has been intimated to BSNL that the speed is within the prescribed limit as per the P.O conditions. But BSNL wants the enhansement in the speed & ready for upgradation required if any. | ZTE | Close
82 | JK | ITI |  | No response from the vendor for repair of faulty IFWTs inspite of making AMC agreement with different vendors as per below detail: 1. With ITI for 15000+10000+4800 IFWTs in three Pos vide P.O nos CE/PO/001/05-06 dated 25-5-2005, CE/PO/009/05-06 dated 27-08-2006, CE/PO/017/06-07 dated 16-3-2007 and AMC for 5 Years from 15-12-2009,13-08-2009 and 25-4-2011 respectively. 2. For 28500 IFWTs vide P.O no. CE/PO/002/06-07 dated 10-05-2006 and AMC date is 29-06-2009 for 5 years. 3. For 19000 IFWTs vide P.O no. CE/PO/014/06-07 dated 03-01-2007 and AMC date is 22-10-2009 for 5 years. 4. For 20000 IFWTs vide P.O no. CE/PO/016/06-07 dated 22-01-2007 and AMC date is 03-04-2009 for 5 years 5. For 25000 IFWTs vide P.O no. CE/PO/018/04-05 dated 24-12-2004 and AMC date is 01-01-2007 for 5 years. 6. For 3000 IFWTs vide P.O no. CE/PO/020/07-08 dated 26-02-2008and AMC date is 10-10-2011 for 5 years Note:-a) In above AMC with vendors except at S.No 5 provision exists for replacement of Batteries but the vendors are not complying, inspite of repeated reminders/notices. Status of faulty IFWTs lying in Srinagar SSAs only of following vendors 1) M/S Teracom faulty FWTS=1564 2) M/S MIC faulty IFWTs=2258 3) M/S XL faulty IFWTS=1327 4) M/S ACD faulty IFWTs=339 5) M/S ITI faulty IFWTs=2508 Similarly faulty IFWTs are available in other SSAs also. Therefore these vendors may be directed suitably to attend the faukts of IFWTs as per AMC agreement. | No details received from J&K circle. | ITI |  |  | Closed
83 | JK | ITI |  | Inspite of making AMC agreement with the vendor M/S ITI there is poor response for rectification of various faults numbering 19 BTS sites faults e.g alarm type faults.Dockets have already been booked in the web tool. | AMC not enetrered into for all the POs.Only 1 PO is under AMC. 3 POs still to be entered. | ITI
84 | JK | Teracomm |  | Against P.O no. CE/P O 009/2010-11 dated 2-2-2011 , 4150 IFWTs were received out of which 500 were issued to DE CDMA Jammu out of this so far 15 sets have been found faulty,5 faulty FWTs have been received back by the vendor but same has not been replaced so far.Vendor may be directed to arrange the replacement as per P O conditions. |  | Not Applicable
85 | KER | ZTE | MSS | 1) Special characters sent from SMSC (characters '<', '>') gets converted into some other characters; thereby changing the content/context of the SMS sent. 2) Alphanumeric SENDER NAME not supported on ZTE Network & because of this telemarketing/service messages sent from ESMEs are not delivered to CDMA mobile handsets (the same gets delivered to GSM handsets). 3) Bulk SMS (SMSC): Reports are not getting generated properly. So It is not possible to find the number of successfully delivered SMS . | 1) Issue has been escalated to R & D team and R&D team is checking the issue and same will be rectified as soon as possible. 2) 2GMSS can not support calling number as ASCII or alphanumeric sender number. If SMS is sent from ESME to BSNL CDMA , SMS will get delivered properly but sender name will show unknown characters. 3) Up gradation of SMSC for the Supporting QAS Backup in TXT file was completed on 20th Jan, Same will be demonstrated by 25th Jan 2012. | ZTE | Open
86 | KER |  | PDSS | P200 is to be commissioned and migration of working BSCBs to TVM PDSN is to be done. | VPN testing is under progress. The same will be completed by 25th Jan'12. Once completed Migration will be carried out. | ZTE | Open | 30th March 2012
87 | KER |  | BSS | Inter BSC Inter Frequency : BTS with different frequency cannot be added in the neighbor-list of BTSs in same BSCB. The same can be done in BTSs working with different 1X-BSCs. | The procedure to do the same has been shared with Circle BSNL . The procedure is different in BSCB software from 1X BSC software. Steps: 1.Complete the Link cell addition first. 2.Configure the neighbour frequency and add the cells corresponding to that frequency. 3.Change the parameter "Is in Critical cell" from "NO" to "YES" in carrier parameter. | ZTE | Close | The procedure has been shared with BSNL and the issue is closed
88 | KER |  | OTA | OTAF: OTAF not yet put into use. | OTA & CSC AT has been completed with pending points ,We have provided the clarification for the pending points. | BSNL | Open | Awaiting for final AT Clearance report from BSNL | Awaiting for final AT Clearance report from BSNL
89 | KER |  | OSS | 1) OSS: Even the 19 reports approved by BSNL CO is not made available. 2) CNO2 (OSS): It is not possible to generate the PN list and Neighbor-list . | 1) For BSCB all 19 reports are available and for 1X BSC, Two reports of EVDO is not applicable for 1X BSC, 14 reports are available and for three reports pach will be implemented by 25th Jan 2012. 2) The PN list and Neibor List is available in OMC. | ZTE | Close | closed
90 | KER |  | WIN | PRBT- M/s OnMobile reports that the *9 activation for copying RBT is not received properly at their server. Also the success rate of CRBT activation through SMS is very low | There is no problem at SMSC end. Once any subscriber send SMS to activate the CRBT SMSC forward that to CRBT successfully. | ZTE | Close | closed
91 | KER |  | MSS | 1) Alarm boxes at the MSCs are not operational. 2) HLRDB number segments are not sorted and is very difficult to locate a level in the number segments. | 1) Alarm boxes are working fine in all 4 MSC's of Kerala. BSNL complaining as New Alarm will not come to Alarm Box, As per observation, Already active alarms are filled memory buffer, once the active alarm rectified, it will get cleared automatically. We suggest BSNL to select only Major and Critical Alarms to Alarm Box to avoid new alarm reporting issue. 2) HLR Database will be updated based on the addition of new levels, Sorting is supported for individual numbers present in the database via Agent tool. | ZTE | Close | 1.closed 2.Closed
92 | KER |  | Operational | All modules of power-plant installed at RTTC faulty and the entire system is shut-down. | Issue has been resolved on 16th Jan'12 by replacing 4 modules. Power plant is switched ON. Rest 4 modules is under shipment, Will be replaced by 15th Feb. | ZTE | Close | closed
93 | KER |  | MSs | Trunk booking service (1586) is not available to the WLL customers | We can implement trunk booking services in CDMA WLL N/W . BSNL has to analyze the 1586 digit and should route to the level 1 Tax in which all the rest part of TRUNK services should depend on TAX only. | ZTE | Close | closed
94 | KER |  | WIN | 1) MNP- CTOP up facility is not available to the port in subscribers. 2) For Porting in to CDMA network, each port in number is to be manually mapped in HLR Data base with corresponding MIN and MDN. So all the port in cases in Kerala is to be manually added in Ernakulam HLR . | 1) ZTE provided Temporary solution to solve the issue, Need to cross check with PIRO. Final solution shall be implemented by 20th Feb 2012 2)Its possible to add portin number by defining Start MIN & MDN and end MIN&MDN . For more clarification ZTE will give prompt support | ZTE | Open | 1. As discussed with Bangalore WIN , the issue is still with ZTE R&D team 2 .ZTE has already provided the support to BSNL
95 | KER |  |  | 127 Nos of Faulty BTS Cards send for repair not yet returned by M/s ITI even after a lapse of one year (Several Reminders were made). | Not correct. Only 20 cards are to be returned back. | ITI
96 | KER |  |  | AMC inr/o V5.2 upgradation equipments supplied by M/s UTL pending for more than 3 months due to non submission of PBG. Also AMC in r/o WLL eqpts against PO11 dated 18.8.2004 expired during Nov 2011. Bills were not submitted by M/s ITI and not yet turned for renewal of AMC agreement. As such AMC may be arranged with M/s ZTE , the manufacture of CDMA Equipments. |  | UTL/ITI
97 | KolTD | ZTE | PDSS | PDSN:  Mobile IP implementation pending for East Zone PDSN.  POS module of Cisco 7609 Router is getting automatically powered off intermittently.  Some of the ZTE Data Cards are not sensing RUIM. Issue pending since last one year.  Essential Spare cards as agreed by Ms ZTE at the time of AMC ( GB Module with Optical Port ) is not supplied yet.  For most of the Cases Session is not disconnected automatically after disconnection of the Data Card causing exorbitant billing for the customers in Limited usages plan. | (1) We checked many times but there is no switching delayed observed. (2) Already demonstrated to BSNL regarding the possible solution. | ZTE | Open | 2012-03-15
98 | KolTD | ZTE | MSS | MSC  There is significant delay in switching (7.5 ~ 11.5 sec). Already informed to Mr. Moin (M/S ZTE) for n/a at the earliest.  Incoming CLI format for voice calls are not proper, sometimes it comes with 0091 and sometimes with 091. | (1) We checked this issue along with Local BSNL many times but there is no switching delayed observed. (2) Already demonstrated to BSNL regarding the possible solution. Need to Modify the necessary configuration at Calling Exchange, Need co-ordination by BSNL to solve this issue. | ZTE | Close
99 | KolTD | ZTE | LIS | 4. LIS 1) LIS AT report submitted with some pending points (submitted to M/S ZTE, Project Manager Mr. Moin on dated 30/09/2011) long back but no response has been received from M/S ZTE. 2) LIS health monitoring/client for report generation not supplied yet. 3) Three remote MSCs connectivity with LIS server still pending( Dimapur & Sillong MSC, Router is not supplied by M/S ZTE for required connectivity) 4) ZTE Engineer is not available at MSC location (at Aizal MSC) for necessary configuration. | 1. Discussion is going on with AT officer, same will be offerred next week for the AT, Major Pending points are related to BOM ( Bill Of Material) The Approved BOM from BSNL HQ is required. 2. Health Monitoring can be done on the Main system only. procedure is already provided to Mr.Sahu. 3. Additional routers are avilable at Agartala & Imphal, BSNL Circles are requested to Divert the unused routed to Dimapur and Shilong for connecting LIS. 4. The work will be completed by 30th Jan 2012 | ZTE | Open | 2012-03-30
100 | KolTD |  | MSS | Roaming in MTNL Service area still pending. | Already tested between Ahamedabad MSC for postpaid service. (No response or updates from MTNL) | ZTE | Close
101 | KolTD |  |  |  CDMA Web based prepaid recharge from BSNL portal still not implemented, but in process and pending with BSNL HQ as informed by Sri Murlidhar GM/ITPC Hyd. |  | BSNL
102 | KolTD |  | Comverse | Automatic Waiver of Rental is not implemented for non service period (Temporary Disconnection) like other operators.( Issue to be taken up with M/s Comverse) |  | BSNL
103 | KolTD |  | PDSS | Prepaid data charging in transition period is not working as per two tier tariff. PDSN SERVER is not sending transition period. | Supported by WIN for time based billing. Same already demonstrated to kolkatta BSNL | ZTE | Close | Closed
104 | KolTD |  |  | 5. IFWT issue :- Circle is facing huge crisis of Good IFWT. Vendor ( VMC) is not ready to take Proportionate AMC as decided by Circles vide Po no CE/PO/006/2009-10 dated 25/06/2009 Quantity received 14940 , Diverted 10000 to Rajasthan, with circle 4940. Po no CE/PO/011/2009-10 dated 30/07/2010 Quantity received 5340 , Diverted 2000 to Bihar , with circle 3340. All IFWT are having Faulty Battery and Circle is not able to sell the same. | (1)MSC never supports Double Forwarding (2) Patch released on 14/01/12, We will do the upgradation on 17th Jan12 | Not Applicable
105 | KolTD |  | MSS | 6. MNP: 1) Two Stage call forwarding is not working after call forwarding patch implementation. 2) PCO reversal (16 KHz local charging) from MSC is going wrong in case of ported in numbers and ported out numbers as there is no LRN based rating implemented in ZTE switch, in case of differential charging. | 1. Not supported. Even previous version was not supported this feature, confirmed by ZTE R&D. 2. Patch implemenetation not sucessful due to some problem in server. Which is resolved, will implement by Feb 1st week. | ZTE | Open
106 | KolTD |  | WIN | SMSC  Bulk promo SMS can’t be broadcasted as SMSC doesn’t supports alphanumeric character in senders address. Earlier ZTE has agreed to upgrade the SMSC by 30.08.2011 ,but again ZTE has deferred the date of up gradation to 17.09.2011 . the said up gradation tried on 21.09.2011 and has failed. Target date: 20.10.2011 in the MOM at BSNL CO, but not yet implemented.  ESME message per unit of time delivered by the Content provider/Access Provider through CDMA SMSC cannot be counted as “ESME Link count” function is not supported. (Counting of SMS of bulk SMS).  Failure list of MDN with failure cause is not coming in case of SMS broadcast, whereas in old CDMA SMSC it was available. Failure list is coming but failure cause is not coming.  LOG file for bulk promo SMS should be maintained to resolve the issue of “DO NOT DISTURB (DND)” in case of any dispute arises. This is not available in CDMA SMSC.  SMS records of a subscriber can’t be queried beyond 30 days in CDMA SMSC. Proper Backup solution not given as proposed in the MOM at BSNL CO.  MO ISD SMS from CDMA sent and delivered, but delivery report is not coming, therefore sender is not able to confirm about successful delivery of SMS. Issue pending with M/S IRIS. IRIS WANTs the content which will displayed to the sender in case of failure, so approved content from BSNL CO is required.  ISD MT SMS from some network to CDMA is not working as our CDMA level are not defined in ISD Partner network , issue pending with M/S IRIS. Testing is going on at zonal level.  *123# ,the CDMA balance query through SMS is not working properly for prepaid subs, “NULL TONE “ to be uploaded by M/S ZTE in CDMA KOLKATA MSC as suggested by M/S ZTE.  Level -1 Services in SMSC not implemented, as MOU with M/S Bharat BPO ( short code 139) for CDMA is not available. | 1. 2GMSS can not support calling number as ASCII or alphanumeric sender number. If SMS is sent from ESME to BSNL CDMA , SMS will get delivered properly but sender name will show unknown characters. 2. We are checking this issue with BSNL. Already send problem to R&D. R&D checking this issue.End of the March-12. 3. MDN list coming but failure cause not coming because current version of Bulk server not support the same. Version is ready, will be implemented by Feb 20th 4 & 5.We already provide solution to meet this requirement like we will provide the QAS server query backup in TXT file. All SMSC upgraded and now QAS Backup generated in TXT file. 6. IRIS Need to take care about this issue. 7. IRIS or BSNL need to take care about this issue. 8. Null tone is already uploaded, also tested *123# service, Only Few cases observed as there was delay in sending SMS and issue related to RF and Location updation of subscriber. Troubleshooting under progress whcih shall be closed by 15th Feb 2012. 9. BSNL need to provide all details/information about the level-1 then we will connect the same. | ZTE | Open
107 | KolTD |  | SMSC | BSNL CO GUIDELINES HAS TO PROVIDE GUIDELINES REGARDING IMPLEMENTATION OF TCCP TRAI Regulation dated 05.09.2011 of PCPR in CDMA SMSC for following two points given below: i) Every Access Provider shall ensure that any commercial communication including SMS, other than transactional messages, is sent to a customer only between 0900 Hrs to 2100 Hrs;” ii) NO Access Provider shall permit sending of more than one hundred SMS per day per SIM . As per TRAI guidelines the above two points to be implemented w.e.f 27.09.2011. | This feature is supported bu Anti-Spam Platform, Technical proposal already submitted to BSNL Co NWP-CDMA section.
108 | KTK | UTL & ITI |  | no Vender is caring the faults booked in their given sites, then what is the meaning in booking the faults in those sites? Is it for name sake? Examples are given below, Kindly bring some effective measures in this regard and help us to maintain the systems properly.
109 | KTK | UTL |  | Sl.no. Docket no. Date fault BTS 1 KTK000073 21-08-2011 GPS Alarm KARWAR 2 KTK000083 20-09-2011 HPA CARD FAULTY BAKKAL (SALKANI) 3 KTK000084 20-09-2011 HPA CARD FAULTY BAKKAL (SALKANI) | AMC not renewed by BSNL & UTL | ZTE | Close
110 | KTK | ITI |  | 1 KTK111015 20-09-2011 TRX CARD FAULTY KAVALAKKI And earlier to this 3-TRX Cards + 1- GPSTM Card + 1- CCM card, total FIVE cards are pending with ITI, those are booked a year and above back. This is about BTS maintenance only. |  | ZTE | Close
111 | KTK | UTL & ITI |  | Other issues Attached in another sheets for UTL & ITI |  | ZTE | Close
112 | MH | Huawei |  | 1) It is observed that some Hawaii Make FWT Model ETS 2222 display ESN “00000000” in NAM instead of ESN inscribed on the back side of FWT.With these instruments, CDMA services can be accessed by NAM programming any CDMA working number without assignment of ESN. In short, these FWTs do not require authentication from HLR for functioning. 2) Speed of EVDO connections is not satisfactory. | This issue reported this week only, we shall check the MSC configuration and close it as soon as possible. | Not Applicable
113 | MH | UTL |  | Sometimes, we are not getting prompt services for the restoration of faults of the equipment which are under AMC. It is therefore requested, kindly instruct M/s. UTL, Bangalore to give prompt service in future. | Kindly mail the docket No to ZTE also after booking to UTL for the prompt support. | ZTE | Close
114 | MP
116 | NE-II | ITI | BTS | Faulty cards to be attended by M/s ITI TRX --- 4 No HPA ---- 11 No PSMC ---- 3 No PSMB ---- 2 No PPM ---- 1 No | faulty cards collection & rectification under progress | ITI |  | 15-04-12 | Card collection under progress
117 | NE-II | UTL | BTS | Faulty cards to be attended by M/s UTL TRX --- 1 No HPA ---- 9 No PSMC ---- 1 No PSMB ---- 10 No PPM ---- 1 No GPSTM ---- 2 No BDM --- 1 No | Card collection from sites under progress & Site rectification done at the same time | utl |  |  | Payment for 30% 2520 K project pending/File progress very slow
118 | NE-II | UTL & ITI | Operational | All the above faulty cards were sent for repair during the first week of Dec 2011. | Work under Progress and will be completed by 10/02/12. | ZTE | Open
119 | NE-II | ZTE | BTS | Eight WLL BTSs are faulty. 1.C HURCHANDPUR 2.LANJING 3.LEIMAKHONG 4.LILONG 5.PAOMATA 6.THOUBAL 7.UKHRUL 8.WANGOI The above BTSs are faulty since last 5 months. The above list has been sent to Sri Prasun Paul CPM/ZTE North east I/C on 17/10/2011 . Last reminder was issued on 5/1/2012. |  | ZTE | Open | 2012-04-20
120 | NE-II |  | BTS | S.No. Issues Pending at Itanagar MSC(WLL) Occurance time Remarks 1 CPSN Card Faulty 19/5/2011 Attended, but fault still exist till date. 2 Hoz MBTS (19.2 Lac Project ) 14/10/2011 Attened on 16/12/2011, but fault exist till date. 3 Tirbin MBTS (19.2 Lac Project ) 14/10/2011 Not attended till date. 4 Kaying MBTS (19.2 Lac Project ) 25/11/2011 Integrated but hardware issue exist from the date of integration 5 Pending MBTS of 19.2 lac project Rumgong, Bene,Baririjo,Mengio,Panchao, Namtok sites still pending. | 1)Bene- power Plant not ready, BB discharge issue at site, 2) Mengio- Power connections not complete from BSNL. 3) Panchao- IDR faulty at site from BSNL. 4)Namtok- Shelter not ready from BSNL at site for ZTE to start installation | ZTE | Close | 2012-04-30
121 | OR |  | LIS | (1) The “LIS” is not working in Bhubaneswar & Cuttack MSC. | Cuttack MSC LIS A/T completed, Bhubaneswar by 28-Jan-12 | ZTE | Close | Closed
122 | OR |  | BSS | (2) FAX is not functioning in Cuttack MSC. | FAX checked and working, need to demonstrate to BSNL. | ZTE | Close | closed
123 | OR |  | BSS/PDSS | (3) The WLL FWT in “Swapping machine’’ is not working. | BSNL to provide the CDMA supported "Swapping Machine". ZTE system support this feature same has been demonstrated in MH-Solapur. | BSNL | Close |  | BSNL to provide the CDMA supported "Swapping Machine". ZTE system support this feature same has been demonstrated in MH-Solapur.
124 | OR |  | MSS | (4) The “ASR” in traffic report is showing less due to the parameters “Early release ringing number” and “vacant number”. What are these parameters and how to minimize it. | Early release ringing number = Release the call before answering ( Missed call) vacant number=Dialling to the number which is not available. Both are subscriber end issue which cannot be controlled by network. | ZTE | Close | Closed
125 | OR |  | MSS | (5) Is there any provision to receive charge band from distant TAX. | Complete Charging and bill processing is taken care by Comverse B&CCS. Need more descriptinon regarding this point | Comverse | Open |  | Complete Charging and bill processing is taken care by Comverse B&CCS. Need more descriptinon regarding this point
126 | OR |  | PDSS | (6) Every prepaid data customer of different plan has fixed data package validity cycle of 30 days.If the subscriber makes the data package valid by top up of required amount within the package cycle then the package validity date counting starts from the starting date of cycle instead of top up date. | If Customer have attached pkg of unlimited/limited data then cycle can't be change. | ZTE | Close
127 | OR |  | PDSS | (7) If the prepaid subscriber did not make its package validate for 2 months or more then its status goes to invalid stage and balance becomes negative and the subscriber under this situation unable to access the internet even after making the top up of required amount.So necessary action should be taken to waive out the negative balance. | If balance is in negative then subscriber can not able to access internet. Suppose if any subscriber 1st cycle from July 30- Aug 29 ,2nd Aug 29 to Sep 28, 3rd 28 sep to Oct 27 .....so on. cycle time will be not change. Suppose subscriber haven't recharge 2-cycle so his 3rd cycle will start from 28th sep to Oct 27 & between this period if he will recharge on 15 Oct then his pkg will be valid for Oct 15 to Oct 27 only ....other days his pkg was invalid. To solve this problem BSNL have introduce unlimited DATA STV for different validity which we have already implemented. | ZTE | Close | Closed
128 | OR |  | BSS | (8) The internet access through the RUIM based CDMA mobile set is not possible. | It is possible to access the internet through RUMI based CDMA mobile while using as modem.WAP 2 feature enabled Handseta are required i:e Samsung Corby etc, Same had been demonstrated in Kerala,KTK and GJ circles. | ZTE | Close
129 | OR |  | MSC | (9) Roaming for EVDO and 1X is not possible in Delhi and Mumbai. | No services of CDMA in Delhi and Mumbai | ZTE | Close
130 | OR |  | WIN | (10) SMS alert should be given to post paid subscriber about their monthly billing and outstanding amount. | One ESME already connected with the SMSC. If subscriber want the billing information then they need to send the SMS to 53333 and they will get the details. And for the automatilcally on mothly basic then BSNL need to provide this kind of application and SMSC need connect this ESME.This ESME need to provide all details to SMSC then SMSC will send the SMS. | ZTE | Close
131 | OR |  | WIN | (11) Tariff change information should be given to CDMA subscriber through sms like GSM. | BSNL need to discuss with ZTE Pre-sales team or Marketing team. | ZTE | Open
132 | OR |  | WIN | (12) In case of prepaid data services after fully utilization of data available in that package, an alert message should be given to subscriber. |  | ZTE | Open
133 | OR |  | WIN | (13) Min-sat facility should be extended to CDMA subscriber. |  | ZTE | Open
134 | PB
135 | RAJ |  |  | Rectification of BTSs faults: The progress of vendor (M/s ITI/ZTE) regarding rectification of BTSs fault is poor. The BTS’s cards (partially affecting) are remaining faulty in between 150-160 numbers regularly even after continuous pursuance with representative of vendors and higher level up to CMD ITI. | As on date 140 faults are there as per BSNL Circle report. | ITI
136 | RAJ |  |  | Repairing/replacement of faulty IFWTs/FWTs: The vendors namely M/s XL Telecom & Energy Ltd, M/s Teracom Ltd, M/s Nextera Telecom Pvt Ltd, M/s MIC Electronics, M/s ACD communications & M/s ITI Ltd are not repairing/replacing faulty IFWTs/FWTs/SMPS/Charger during the AMC period even after continuous pursuance with vendors at various levels and commitment given in the meeting by vendors. | Details not available with ITI. | ITI
137 | RAJ |  |  | Vendors have refused totally to replace / repair the faulty internal battery of SMPS units of IFWT under AMC. | Not related to ZTE | ITI
138 | RAJ |  | WIN | Recharging problem of subscribers through C-TOP UP: Port-in subscriber can not recharge / top up through C-TOP UP. In addition, all CTOP-UPs are not connected so the subscriber of one zone visited to other zone can not recharge their mobile using CTOP-UP. | Not related to ZTE | BSNL | Close
139 | RAJ |  |  | Sancharsoft implementation: Sancharsoft implementation is pending. Due to which creation of new connections through franchisee channel become difficult. | Not related to ZTE | BSNL
140 | RAJ |  |  | Three MSC with HLR namely Alwar, Bhilwara and Jodhpur can be spared in Rajasthan for diversion else where. | Not related to ZTE | BSNL
141 | RAJ |  |  | Earlier, there were heavily discounted promotional schemes continuous for almost one year like 50% addition talk value on top up and reduce price of annual local azadi pack STV of Rs. 1500/- instead of Rs. 2000/-. Now, these are totally withdrawn. It is requested that there will be middle path that 20% extra talk time on top ups( to offset free validity in GSM with each top ups). | Not related to ZTE | BSNL
142 | TN | ZTE | OSS/LI | Works to be Completed by M/s. ZTE: a. OSS implementation at Madurai b. LI implementation in Madurai, Coimbatore, Salem & Pondicherry c. CSC at Salem and Pondicherry | a. OSS AT is in progress b.All TN MSC's are connected to LIS Ernakulam. | ZTE | Open | 25.03.2012
143 | TN | ZTE | MSs | MSC HLR MP server at Madurai MSC I is frequently hanging (for the past six months) and it is made reset manually. The fault could not be rectified by M/s. ZTE . It is learnt that the same problem exists in MSCs in other circles supplied under the above project. | No such issue in any other MSC, As per Regular maintanance, MP Switchover and MP reset need to carry out. Same details are already shared with BSNL. | ZTE | Close | The MP change over being done during regular maintenance. No issue observed for the past two month.
144 | TN |  |  | 2. Replacement of Faulty Cards accumulated during past six months i)Madurai MSC a. BTS Fans – 40 b. GPSTM card – 5 c. HPA -10 d. KVM switch monitor -1 e. PPM card -2 f. BSC server spare cards taken for replacement are not recuped. ii) Coimbatore MSC: a. SAM -2 ( One since 15-12-2009 & other from 3-8-2011) b. CHM -1 c. TRX card – 1 d. HPA -1 iii) Pondicherry MSC: a. HPA-6 b. GPSTM-4 c. SDT-1 d. TCM-2 e. PSMB-1 f. ESVM-6 g. TRX-1 | These cards are to be returned to ITI/ZTE/UTL for repair and return. | BSNL |  | Under being provided regularly, except fans. KVM Switch attended. Coimbatore SAM Card provided to ITI.
145 | TN | ITI |  | 3. Delay in reentering of AMC for PO 24 by M/s. ITI: AMC for PO No. CE/PO/024/04-05 dtd 7-3-2005 entered on 23-06-2010. Due to expansion/ up gradation of CDMA WLL equipments in various POs , it is necessary to revise the AMC agreement as per item (7) of corporate office letter no 190-03/202-MMD/ VOL II dt 01.11.2010. Hence termination of AMC was issued to M/s ITI on 07.03.2011. As per corporate office letter no 190-03/202-MMD/ VOL II dt 01.11.2010 the latest approved rate ie @ 0.356% per annum and as per terms and conditions of MSC based WLL CDMA equipment (TE300) is applied for calculation of AMC charges and it is to be entered for the period of five years from the current date. Even though circle is ready to enter AMC M/s ITI is not responding. | ITI does not accept this. Terminating the old AMC midway and re entering into AMC at 0.356% is not acceptable to us. BSNL CO to take a decision. | ITI
146 | TN |  | OSS | Viewing of OSS report by field units. Presently the reports of all BSCB and MSCs through OSS can be obtained from the OSS server available at Madurai only. Daily monitoring of traffic by field units is essential for immediate clearance of fault/congestion Hence instantaneous viewing of reports by SSAs by logging into the OSS server is essential. M/s ZTE has to co-ordinate on this issue. Moreover OSS reports for BSC 1X(9nos) is not obtainable. | Local BSNL need Clients in every SSA's, which is not available. We suggest BSNL to Install 1 FTP server and dump the reports in to FTP for accessing by Field units. Upload the reports to BSNL portal and same can be downloaded by field units. | ZTE | Open | TSD Team to provide to respond
147 | TN |  | WIN | Tariff plan creation in WIN for a particular circle alone. Certain prepaid plans which have demand in TN Circle have been taken with BSNL HQ and got approved. But these Plans could not be created in WIN for TN circle alone. It is found that Plans can be created in WIN for entire Zone. Delay in creation and implementation of promotional offer extension deprives provision of new connections. | WIN already support Tariff plan for a particular circle alone. | ZTE | Open | TSD Team to provide to respond
148 | TN | ZTE | WIN | Post paid Roaming billing issues is yet to be solved. M/s ZTE is to extend co-ordination to M/s COMVERSE for testing and Launching. | ZTE alredy supporting BSNL and Comverse for adding new levels reguraly. | ZTE | Close | BSNL & WLL Teams are continuously extenting supporting each other whenevr new levels are added
149 | TN | ITI |  | Two nos of OF Repeaters and two no of RF Repeaters supplied by M/s ITI is to be repaired. | Docket not available. However, fault replacement can be given after docketing. | ITI
150 | UA | ZTE & ITI | bts | As per operational point, it has been noticed that there is always shortage of spare cards at M/s ITI/ ZTE end, due to which fault rectification time increases in most of the cases. The SSA can book fault on M/s ITI site-http://180.151.36.6/cdmabg/ but M/s ITI/ZTE has kept docket closing work in their control. Docket closing should be done at the level of person, who has actually booked the fault. Vendor, after resolution should give its compliance in remarks column, which should be verified by docket booking person & then only docket should be closed. This practice is being followed by GSM Vendors in Mobile wing. As such docket booking application must be modified to this extent. | As on date only 4 faults are pending. | ZTE | Open
151 | UPE | ZTE, UTL & ITI | MSS | Sl no Issues Call log number Report Date 1 Any CDMA number when programmed on IFWT with 00000000 ESN will work, which needs authentication with ESN ZOO3201111180113 14-10-2011 2 There is Alarm in Comm. Board of MSC2 ZOO3201111180126 24-11-2011 3 One HLRDB server of MSC2 is faulty RS20111224575254 24-12-2012 4 SWAP Machine is not working on IFWT/FWT RS 20111230661886 29-12-2011 5 LIS services not working on mobile levels ZOO 3201111180116 | 1. To be checked with Handset vendor. 2. resolved 3. resolved 4. Solution given to bsnl, BSNL to arrange the required hardware. | ZTE | Close
152 |  | ZTE, UTL & ITI | BTS | Various alarms are not cleared timely and adequate attention is not being given by M/s ITI/UTL/ZTE. All equipments are either under AMC or Warranty with ITI/UTL but no staff is posted by these vendors because they have done agreement with ZTE to take care off AMC/Warranty. But ZTE also has removed all their manpower from UP (E) Circle. This is causing serious setback to O&M of CDMA network.ZTE may strengthen the manpower instead of reducing it to zero. | ZTE trained staff are available in circle to address the Issues, As required by BSNL Co N.W.O the detail list of ZTE staff will be submitted for PAN India. | ZTE | Close
153 | UPW | ZTE | OSS | Escalations on OSS platform is to be streamlined at various level based proforma.M/s ZTE has to be pushed on this.Sufficient inputs have been given to them and they are working on it |  | ZTE | Open
154 | UPW |  | Operational | Manpower deployment iro AMC in the circle has to be increased-this is an important issue to be addressed. | ZTE trained staff are available in circle to address the Issues, As required by BSNL Co N.W.O the detail list of ZTE staff will be submitted for PAN India. | ZTE | Close
155 | WB |  |  | PPC: -
156 | WB |  | MSS | When subscriber in GP1 or GP2 state, having negative balance, recharges his account, validity date extends but status of | We are checking this issue | ZTE | Open | 25-01-12
157 | WB |  | WIN | There is no option to know the EXPIRY DATE of STV or NEXT RENT DATE of package by subscriber. | Current version does not support. | ZTE | Close
158 | WB |  | WIN | No call is maturing with Prefix +91 from any MSC of East Zone. | Already upgrade Kolkata And solved. | ZTE | Close | Solved
159 | WB |  | WIN | No proper document is provided to implement accumulative bonus plan. | Already Submitted all document long time before. WB BSNL need to provide the specific problem in the document. | ZTE/BSNL Circle. | Open
160 | WB |  | WIN | Free Call service feature is available only for 5000 subscribers but according to PO under PPC bonus scheme this facility | New Requriement. Require disucssion between BSNL and ZTE presale team. | ZTE | Open
161 | WB |  | WIN | No log is coming for STV recharge and no count is coming in statistics for STV recharge. M/s Pyro is not ready to implement | As per 24-25-Nov2011 Meeting M/s ITI/ZTE informed that ITI/ZTE need serial no. for every command. BSNL need to discuss with other third party side who responsible for STV recharge,that they need to send a serial no. for every single command then only they can get it in the log. Respective IN incharge shall get it implementated in respective C-TOP system by 7-Dec-2011 No count is coming in statistics for STV recharge-New Requirement. | ZTE | Open
162 | WB |  | WIN | No back-up of SCP1/SCP2/SMP are not possible due to unavailability(obselete) of TAPE(cartridge). | As per MOM of 24-25-Nov2011 meeting:- ZTE already shared the contact person details to get the TAPE drive Contact Details:-sreekanth.pandikunta@wipro.com | ZTE | Close
163 | WB |  | WIN | Restoration of services in SCP1/SCP2/SMP with back-up is not shown. | As per MOM of 24-25-Nov2011 meeting:- M/s ITI/ZTE informed that it has been demostrated to BSNL long time before and ZTE have shared document with BSNL. | ZTE | Close
164 | WB |  | WIN | No AOC is coming for 'rent deduction' or 'rent deduction failure'. | As per MOM of 24-25-Nov2011 meeting:- M/s ITI/ZTE informed that Current version does not support. | ZTE | Close
165 | WB |  | WIN | DATA CDR is not coming in Bill.exe. Although M/s ZTE charged BSNL for providing this Application software. | As per MOM of 24-25-Nov2011 meeting:- M/s ITI/ZTE informed that Data CDR is availble in CDR server. | ZTE | Close
166 | WB |  | WIN | SMS STV count once given in IN,does not differentiate between local,STD or ISD | Supported by the system. Already explain and given the procedure to Vadodra team,After Implementaion by the said procudure the SMS STV counts for Local,STD and ISD can be differinated. Vadodara BSNL is not accepting the procudure/solution given by ZTE. | ZTE | Close | closed
167 | WB |  | WIN | Code wise charging through C TOP up not implemented. | This is a new Requirement.Commercial to be discussed. | ZTE | Open
168 | WB |  | WIN | Multi FNS group required for having different call rate in different CUG |  | ZTE | Open
169 | WB |  | WIN | FRC implementation |  | ZTE | Open
170 | WB |  |  | When subscriber recharge through C TOP up , ADD mode is not working…. M/s Pyro to solve | This is Pyro Issue. | ZTE | Open
171 | WB |  |  | Promotional offers such as '' 50% extra talk value on Flexi top up ''could not be implemented by M/s Pyro | This is Pyro Issue. | ZTE | Open
172 | WB |  |  | DATA SERVICE: -
173 | WB |  | WIN | Limited and Unlimited DATA STV features are tested sucessfully. M/s ZTE(for IMP Upgradation and STV log) and | As per MOM of 24-25-Nov2011 meeting:- M/s ITI/ZTE informed that we are ready for the same. We need just a night activity for the log. Already informed to BSNL.Will be done in short span of time. BSNL CO. told that the activity shall be completed by 30-Nov-2011 by all concern. Still WB BSNL not provide the permission to upgrade WIN. | ZTE/BSNL Circle. | Open
174 | WB |  |  | M/s Pyro(for MML command configuration and testing) have to implement it through C Top-Up.------ M/s Pyro to solve | This is Pyro Issue. | ZTE | Open
175 | WB |  | WIN | Information of consumption of DATA of 'package based subscriber', when queried from PPC Client, is coming wrong. | As per MOM of 24-25-Nov2011 meeting:- M/s ITI/ZTE infomed that such query can be done from "Fee charge" in PPC interface. | ZTE | Open
176 | WB |  | WIN | All India EVDO/NIC/Voice roaming to Delhi and Mumbai region is not implemented. | As per my knowledge Voice Roaming testing with MTS is going on. | ZTE | Open
177 | WB |  |  | Call Conference, Call forwarding and Call Waiting: -
178 | WB |  | MSS | Short code for Activation and Deactivation of Call forwarding and call waiting are not uniform in all CDMA MSCs. | Different circle are using different short codes as per their own requirment, Required BSNL Co to streamline the same for all MSC's. | ZTE/BSNL Circle. | Open
179 | WB |  |  | CRBT: -
180 | WB |  |  | Short Code 56777 and 56799 are not implemented for CRBT/IVR --- M/s On mobile to solve | This is a M/s OnMobile issue. | ZTE/BSNL | Open
181 | WB |  | MSS | *9 feature for CRBT activation is not implemented.--- M/s ZTE to solve | ZTE MSC supports *9 copy feture , Already tested with IMI, Problem is with OnMobile , BSNL is requested to call a meeting with OnMobile so the same can be discussed and can be resolved. | ZTE/BSNL | Open
182 | WB |  |  | RBT GUI is not available to monitor and handling CRBT complain subscriber of CDMA.-- M/s On mobile to solve | This is a M/s OnMobile issue. | ZTE/BSNL | Open
183 | WB |  |  | WVPN: -
184 | WB |  | MSS | CRBT activation is not possible through SMS of WVPN subscriber. | As per discussion with OnMobile There is no issue at WIN and SMSC end. OnMobile is working on the same, | ZTE | Close
185 | WB |  | WIN | CTD: - Tested and given to ZTE for feedback and Customization for BSNL -- No Feedback from ZTE. | Charging according to cellid and timespan already realized in PPC, Post-paid user do not need to register IN, directly charging by the billing system according to CDR. | ZTE | Open | As discussed in 24-25-Nov-2011 HQ Meeting:- BSNL CO asked ZTE to implement all the service in WIN and also give one presentation to BSNL CO on Service features.. Vadodara and Bangalore IN Team need to check all issues which is raised by Kolkata BSNL and report need to submit by 20-Dec-2011 Update on 2-April-2012:- We have already given presentation to BSNL CO. All short service has been implemented. Now BSNL need to test and provide the feedback.
186 | WB |  | WIN | Operational manual for CTD is required. - This will enable operator to create CTD service and manage it properly | Charging according to cellid and timespan already realized in PPC, Post-paid user do not need to register IN, directly charging by the billing system according to CDR. | ZTE | Close
187 | WB |  | WIN | Cell/time Discount announcement - The CTD customer should get announcement for which type of discount he is getting. | Charging according to cellid and timespan already realized in PPC, Post-paid user do not need to register IN, directly charging by the billing system according to CDR. | ZTE | Close
188 | WB |  | WIN | Proper announcement is required in national and regional language. - Announcement should be based on the service area .there should be hindi, English and local language for each service area. | Charging according to cellid and timespan already realized in PPC, Post-paid user do not need to register IN, directly charging by the billing system according to CDR. | ZTE | Close
189 | WB |  | WIN | Cell discount and time discount simultaneously. - Test is required for CTD Subscriber that it will get cell discount and time discount simultaneously or not. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
190 | WB |  | WIN | Management by subscriber - The customer must be able to subscribe and unsubscribe CTD service for him through IVR. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
191 | WB |  | WIN | Call duration Increment in case of free number - If a customer is having CTD service and if he is dialing any free number that his call duration must not increase because it will effect on his discount pattern . For example he is having discount by duration. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
192 | WB |  | WIN | CTD service must be made available for both prepaid and postpaid customers. - CTD service should be available for both prepaid and postpaid customers. right now it is available only for postpaid customers. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
193 | WB |  |  | FCS: - Tested and given to ZTE for feedback and Customization for BSNL -- No Feedback from ZTE
194 | WB |  | WIN | PARAMETER ---(A)MAX TIME LIMIT (B)DAILY CALL LIMIT (C) MONTHLY CALL LIMIT - MASTER ACCOUNT SUBSCRIBER HAVE TO VISIT CSC OF BSNL OFFICE FOR SETTING OR CHANGING EVERY TIME THESE PARAMETER. IT MUST BE FROM IVR FLOW. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
195 | WB |  | WIN | DELETION OF ANY NUMBER NOT POSSIBLE - PROVISION FOR DELETION OF NUMBER SHOULD BE THERE | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
196 | WB |  | WIN | FROZEN PERIOD IS FIXED INTERNALY IN SYSTEM. IT CAN NOT BE CHANGED - LIFE CYCCLE OF NUMBER SHOULD BE CONFIGURABLE IN GUI | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
197 | WB |  | WIN | NO OPTION FOR CHOOSING PREFERRED LAGUAGE - OPTION MUST BE IN IVR | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
198 | WB |  | WIN | PASSWORD MANAGEMENT - FOR CONFIGURATION OF PARAMETER MANAGEMENT ONLY SYSTEM ADMINISTRATOR CAN MANAGE. PASSWORD IS ERQUIRED FOR IT. BUT BSNL WANT SUSCRIBER CAN ALSO MANAGE PARAMETER THROUGH IVR. PASSWORD IS REQUIRED FOR MASTER ACCOUNT TO MANAGE HIS PARAMETER. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
199 | WB |  | WIN | FREE NUMBER AND SPECIAL NUMBER - AT PRESENT FREE NUMBER AND SPECIAL NUMBER CAN BE CONFIGURED IN ONE BOX IN GUI. IT SHOULD BE IN DIFFERENT BOX. | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
200 | WB |  | WIN | No announcement, when amount for making call is not sufficient and subscriber is unable to call - Announcement required | This feature already realized in PPC free call function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
201 | WB |  | WIN | Call disconnected when amount exhausted without notification - Notification required |  | ZTE | Open
202 | WB |  | WIN | No announcement when daily call limit reached or exceed - Announcement required | We will re-provide DOC about this service on 15th Feb. | ZTE | Open
203 | WB |  | WIN | No announcement when monthly call limit reached or exceed - Announcement required | Already support. | ZTE | Close
204 | WB |  | WIN | Interzone/scp number as family number - Test Pending | Not support,now we support base on different called numbers different languages. | ZTE | Open
205 | WB |  | WIN | FCS subscriber have SMS and DATA facility - Test Pending | Not supprt, FPH is faced on enterprise not single person, so any configuation should be done at hall. | ZTE | Open
206 | WB |  | WIN | FPH: - Tested and given to ZTE for feedback and Customization for BSNL -- No Feedback from ZTE | Not support, if off-net user dial BSNL 800, it will cause charge twice times. | ZTE | Close
207 | WB |  | WIN | Operational manual for FPH requires - This will enable operator to create FPH subscriber and manage it properly | Not support, WIN protocol call reason will not report to SCP. | ZTE | Close
208 | WB |  | WIN | Call routing plan based on origin of call is required. - The subscriber’s call from a defined area must land on the same area’s FPH number. for example if subscriber is calling from west Bengal than his call must land on west Bengal call centre of FPH number. | Already support, define transfer number as Voice box number. | ZTE | Close
209 | WB |  | WIN | Proper announcement is required - Announcement should be based on the service area .there should be hindi, English and local language for each service area. | We will re-provide DOC about this service on 15th Feb. | ZTE | Open
210 | WB |  | WIN | Service management access through IVR - FPH Subscriber(administrator) should have choice to manage— a)maximum duration of call b)no. of incoming call to FPH no. over a period c)a call threshold can be defined d)no. of simultaneous call to FPH no e)routing and timing administration such as he should be able to manage his incoming calls based on time, week , holiday | To support this feature,Need New System Automatic Call Distribution System. | ZTE | Open
211 | WB |  | WIN | Call from other switches of BSNL (GSM/PSTN/CDMA) and other network(GSM/PSTN/CDMA) - Testing is required with main number so that it will be possible to test call to FPH number from other networks as well as from other switches of BSNL network. | IN system does not support. | ZTE | Open
212 | WB |  | WIN | call routing in case of subscriber is busy or is not answering within a given period of time. - If termination number is busy/does not reply within given time period call will route to alternate number |  | ZTE | Open
213 | WB |  | WIN | Voice box - test pending |  | ZTE | Open
214 | WB |  | WIN | Explanation of following terms requires 1)call with preference 2)prefix group name 3) prefix group management 4) Max. of forward number 5)Max of service branch 6)Average of service branch 7)Max of calling area 8)Average of calling area 9)Max of forbidden number - As theses terminologies are not clear because manual given is in very brief. | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
215 | WB |  | WIN | Call queuing - When all operators of FPH are in busy condition. next few callers should be in call waiting condition as soon as any free line is detected the call is answered in cyclic manner (first come first serve basis). | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
216 | WB |  | WIN | Incoming grey list - This feature should be provided. If a calling line is added in grey list than, a pin is associated with it and when this caller will call FPH number, pin will be asked for authentication. | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
217 | WB |  | WIN | PRC: - Tested and given to ZTE for feedback and Customization for BSNL -- No Feedback from ZTE | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
218 | WB |  | WIN | Issues of PRC(none of following facilities could be shown during test) | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
219 | WB |  | WIN | Single All India Number - Conversion of Public IP's to Private IP's are still pending in respect of MSC/BSCBs | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
220 | WB |  | WIN | Time of Day/Time Interval Routing - allows organizations to route calls to different answering locations, depending on the time of day. For example, if your customer service department is closed, you can route callers to alternate location | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
221 | WB |  | WIN | Day of the Week Routing - Calls can be routed not only as per the Time of the day but also as per the type of day | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
222 | WB |  | WIN | Origin Dependent Routing - Calls can be routed to set of destinations based on the origin of the call | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
223 | WB |  | WIN | Call distribution - allows organization to route calls based on staffing levels. If one location is short-staffed, you can split calls such that these calls go to two or more answering locations. The call split is based on a percentage distribution that you designate. | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
224 | WB |  | WIN | Line hunting - allows organization to have one or more installations where the call may be answered | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
225 | WB |  | WIN | Call limiter - Restricts maximum number of simultaneous calls and this helps organization to dimension resources | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
226 | WB |  | WIN | Call Queuing - – enables calls meeting busy condition or reaching call limiter to be placed in a queue and as soon as free condition is detected the call is answered | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
227 | WB |  | WIN | Condition based routing - Calls at the destination can be re-routed to a different destination number in following conditions (1) Busy (2) No Answer (3) Reached call limiter. | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
228 | WB |  | WIN | Interactive voice response - The IVR routes calls to the appropriate person or department based on keypad inputs selected from the menu options as defined by the service subscriber. | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
229 | WB |  | WIN | Black & White List - allows organization and operator to selectively block incoming calls from specific originating areas | This feature already realized in PPC special tariff function, Billing system get CDR from MSC deal with post-paid users. | ZTE | Open
230 | WB |  | WIN | Incoming Grey list - When a calling line is added in the grey list , a PIN is associated with it. When a caller from grey list access the service , a PIN is asked for authentication |  | ZTE | Open
231 | WB |  | WIN | charging calling parties - the calling parties from any networks like CDMA, GSM, PSTN etc who will call to PRC number, are to be charged |  | ZTE | Open
232 | WB |  | WIN | Intimation to calling party - as the call rate for calling to PRC numbers is normally high for that the calling party is to be intimated as announcement before connecting call. |  | ZTE | Open
233 | WB |  | WIN | IVR Flow - The subscriber will be given some management codes and password. Using that he can add/delete/modify any features into his premium rate number |  | ZTE | Open
234 | WB |  | WIN | Billing - All the calls made by subscriber using his premium rate number will be billed by the IN platform |  | ZTE | Open
235 | WB |  | WIN | Location based, time based and personal charging are not as per call flow what ZTE have shown for PRC number |  | ZTE | Open
236 | WB |  | WIN | Conversion of Public IP's to Private IP's are still pending in respect of MSC/BSCBs |  | ZTE | Open
* In case remark response is not provided by M/s ZTE, M/s ZTE will reply remark and target time

## Summary Updates
Subject: Minutes of meeting held at BSNL CO, New Delhi on 23-01-2012 with all the CDMA vendors on Operational Issues
SL no | Description of the issue | Under ZTE/ITI/UTL/BSNL Scope | Issue Closed/ Pending | Action Plan/Update by Circles | Circle Remarks
1 | Spares Faulty Cards 1. All faulty cards should be repaired with in 1 month 2. ITI will replace all the faulty cards of Rajasthan within 15 days 3. Sufficient spares should be provided to field unit in all Circles by Vendors 4. M/s ZTE, M/s ITI & M/s UTL will provide the detail of No. of Faulty card received, replaced and pending card on daily basis on their Portal-Action to be taken by M/s ITI, M/s UTL, M/s ZTE 5. Circles will provide the certificate of all the faulty cards to ITI/ UTL/ ZTE with the copy to BSNL Corporate office and Vendor will repair all the faulty cards | ZTE/ITI/UTL | Open | Details of all faulty spares/cards will be provided by 4-Apr-12 as already communication in progress with circles for collecting the details. Rest circle updated are attached.
2 | Large No of Dockets are pending. 1. 1100 nos of faults pending in ITI portal 2. 330 nos of faults pending in UTL portal | ITI/ZTE UTL/ZTE | 1. Open 2. Open | (1) ITI Open Dockets: Under ZTE Scope(Total faults-759, Open-266, Close-493) Under ITI Scope(Total Faults-237, Open-205, Close-32) Under BSNL Scope(Total faults-104, Open-47, Close-57) (2) UTL Open Dockets: Under ZTE Scope(Total faults-240, Open-86, Close-154) Under UTL Scope(Total faults- 66, Open-57, Close-9) Under BSNL Scope(Total faults 24, Open-20, Close-4)
3 | Shortage of Vendor technical Staff. 1. Circle wise Structural information regarding Technical Staff posted by M/s ZTE, M/s UTL, M/s ITI in all Circles 2. Various alarm are not cleared timely and adequate attention is not given by Vendors | ZTE/ITI/UTL | 1. Close 2. Close | (1) All details of the technical manpower is already given to the UTL & ITI. (2) Already given the target dates for the pending points, Need the confirmation mail of the open faults directly from BSNL also while booking the docket in ITI/UTL portal so that immediate action will be taken.
4 | MSC Issues Faced by the Circles. 1. Several Hard disk faults at Guwahati MSC location 2. Three HP servers (i.e. Map server, HLR O&M server and VLR ADC server under 630K line project) and four hard disks (3 cluster hard disks and 1 VLR hard disk) are lying faulty in MSC Hisar 3.Call forwarding restriction to other operators- still to be implemented by ZTE – Assam 4. Call forwarding is allowed local to STD only | ZTE | 1. Open 2. Close 3. Open | (1) New Hardisk already ordered & will be close by 20th Mar. (2) Servers rectified on 17-01-12 and was informed to SDE MSC Sunita Araora Madam, 2 Hard disk supplied to hisar , 2 under process (3) In progress PAN India
5 | OSS Issues faced by the circles. 1. 13 OSS reports relates to MSS will be implemented and taken from the system 2. Several issues relating OSS are still to be resolved by M/s ZTE 3. MSS Jorhat Router is not working since Aug’11 4. CNO Report not available for Nagaon 1X BSC & Barpeta Rd.BSCB 5. BTS status not getting updated for Silchar, Tezpur & Dibrugarh 1X BSCs 6. Servers faulty at Hisar MSC | ZTE | 1. Close 2.Close 3.Close 4.Close 5.Close 6. Close | (1) We have already sent the letter to all circles & implemented in all locations. (2,3,4,5) Nagaon 1X BSC is connected to OSS and when media is having problem then only reports are not readily available. & Barpeta Rd.BSCB media fluctuation. (6) Servers rectified on 17-01-12 and was informed to SDE MSC Sunita Araora Madam, 2 Hard disk supplied to hisar , 2 under process
6 | SMSC issues faced by the circles 1.Special characters sent from SMSC (characters '<', '>') gets converted into some other characters; thereby changing the content/context of the SMS sent – Kerala 2.Alphanumeric SENDER NAME not supported on ZTE Network & because of this telemarketing/service messages sent from ESMEs are not delivered to CDMA mobile handsets (the same gets delivered to GSM handsets) – Kerala 3.Bulk SMS (SMSC): Reports are not getting generated properly. So It is not possible to find the number of successfully delivered SMS | ZTE | 1. Open 2. Close 3. Close | (1) Issue has been escalated to R & D team and R&D team is checking the issue and same will be rectified as soon as possible. (2) 2GMSS can not support calling number as ASCII or alphanumeric sender number. If SMS is sent from ESME to BSNL CDMA , SMS will get delivered properly but sender name will show unknown characters. (3) Up gradation of SMSC for the Supporting QAS Backup in TXT file was completed on 20th Jan, Same will be demonstrated by 25th Jan 2012.
7 | EVDO Services 1.Data access through RUIM based HHT is not possible in Orissa, Kol TD, AP, JHK, Assam 2. Speed of EVDO connection is not satisfactory (Posibility of upgradation of BSC) 3. Postpaid / limited plan customer are not able to check their data usage -HP 4. SMS alert should be given for Billing, traffic etc. 5. Some EVDO BTSs have no data flux in some PCMs even PCMs are OK 6. FAX not working in 630K EVDO BSC | ZTE | 1. Close 2. Close 3. Close 4. Close 5. Close 6. Close | (1) WAP 2 feature enabled Handsets are required i:e Samsung Corby etc, Same had been demonstrated in Kerala,KTK and GJ circles. possible to access the internet through RUMI based CDMA mobile while using as modem. (2) The downloading speed has been tested on various BTS sites & same has been analyzed by ZTE Technical team & the reason for poor downloading speed is loading of BTS. Same has been intimated to BSNL that the speed is within the prescribed limit as per the P.O conditions.But BSNL wants the enhansement in the speed & ready for upgradation required if any. (3) BSNL need to discuss with ZTE Pre-sales team or Marketing team. (4) One ESME already connected with the SMSC. If subscriber want the billing information then they need to send the SMS to 53333 and they will get the details and for the automatilcally on mothly basic then BSNL need to provide this kind of application and SMSC need connect this ESME.This ESME need to provide all details to SMSC then SMSC will send the SMS. (5) Patch implemented, need to demonstrate to BSNL. (6) Patch is Implemented will be demonstrated to BSNL by 10th Feb 2012.
8 | PDSN Issues Faced by Circles 1. Mobile IP implementation pending for East Zone PDSN. 2. POS module of Cisco 7609 Router is getting automatically powered off intermittently 3. Some of the ZTE Data Cards are not sensing RUIM. Issue pending since last one year ( Action by ZTE- replacement of card as circle provide such cards.) 4. Essential Spare cards as agreed by Ms ZTE at the time of AMC ( GB Module with Optical Port ) is not supplied yet. 5. For most of the Cases Session is not disconnected automatically after disconnection of the Data Card causing exorbitant billing for the customers in Limited usages plan. M/s ZTE to decrease the session time. | ZTE | Open | (1,2,3,4,5) We checked many times but there is no switching delayed observed. (2) Already demonstrated to BSNL regarding the possible solution.
9 | General Issues faced by Circles 1. No SMS based fault escalations mechanism provided. BSNL C.O. have already given direction to left out Circles. 2. Unrestored BTS alarm when saved, save one BTS alarm in BSC-1 and BSC-2(i.e 630K Project BSC) 3. Chip is not installed in GPSTM card in many BTSs as a result GPSTM Resets thus hampering call & 1x data 4. Temperature sensors & smog sensors are neither not installed or not working in many BTSs 5. All modules of P.P installed at RTTC faulty & entire system is shut down. 6. Various test tools, analyser etc are not working | M/s ZTE | 1. Open 2. Close 3. Open 4. Close 5. Close 6. Open | (1) SMS is sent through the alarm box to all the concerned people's numbers added through the BSC OMC. Same can be configured. The alaram BOX supplied are for MSC's are not fully utilised, Spare alarm BOX can be utilized for BSC-1X alarm escalation by SMS. (2) All BTS need to be selected while saving the alarms. (3) GPSTM chip: Work is under progress in circles (4) Temperature sensor: Not docketed on ITI website, Circle to register the call log (5) All 7 modules has been replaced out of 8 modules rest will be replace by 25-Mar-12 (6) It is under Working condition in AN Circle, Some are already sent for repair to Agilent.
10 | FWT Issues faced by the Circles 1. ITI not attending FWT Faults 2. Faulty FWTs not being repaired despite AMC 3. FWT can not booked in ITI Portal | M/s ITI | 1. Open | (1,2,3) BSNL to provide the CDMA supported "Swapping Machine". ZTE system support this feature same has been demonstrated in MH-Solapur.